## Project Logframe
Level | Summary of objectives | Indicator | Means of Verification | Assumptions
Programme Outcome (project goal) | Strenghtened child protection systems in Ghana to adequately prevent, respond to and manage child rights and protection issues. | % of children rights violation cases or issues as report by DOVSU | DCI Evaluation Report | Stakeholders’ willingness to work with issues of child right. Availability of Funding for the project
Outcome 1 | Improved policy formulation and implementation by government including the district assemblies of Ghana aimed at filling child protection gaps | % of communities engaged in drafting and formulating CP policy | DCI Evaluation Report DCI Annual Monitoring Report | Stakeholders’ willingness to work with issues of child right. Functional in-coutry CSO coalitions Availability of Funding for the project
Outcome 1 |  | % of child protection policy, planning or practice changes that have been informed by evidence from civil society | DCI Evaluation Report DCI Annual Monitoring Report | • Favourable cooperation of stakeholders on issue of children right •Functional in-coutry CSO coalitions •Availability of Funding for the project
Output 1.1 | Improved capacities of staff to lobby for and draft child protection policy that will guide the child protection system strengthening initiative in Ghana | # of staff who have capacity to undertake advocacy | DCI semi-annual and annual reports | •Willingness of communities to work with issues of child right and engage duty bearers. •Availability of Funding for the project
Output 1.1 |  | # of DCI staff trained in child protection system strengthening | DCI semi-annual and annual reports | •Availability of Funding for the project
Activity 1.1.1 | Conduct legislative reviews to identify gaps and evidences for law reforms
Activity 1.1.2 | Conduct legal research and examine the efficacy of the Ghana Children’s Act and other relevant laws
Activity 1.1.3 | advocate for legal reforms with the view of harmonising laws with the new child protection policy
Activity 1.1.4 | Contribute to the drafting of the new bills and also lobby for the passage of the new bills into laws collaboration with UNICEF, GP CSC and other influential CSOs and coalitions
Activity 1.1.5 | Disseminate the new policies and laws particularly in local communities targeting both adults and children/youths, in collaboration with CBOs, journalists and other CSOs and relevant MDAs
Output 1.2 | Capacity of government institutions and relevant community based structures built in Child rights & protection Policies | # of community based organisations trained in incident management and referrals | DCI semi-annual and annual reports | willingness of CBO to be available for training and apply knowledge gained
Output 1.2 |  | # of government institutions/structures trained in Child rights & protection Policies | DCI semi-annual and annual reports | willingness of government institutions to be available for training and apply knowledge gained
Activity 1.2.1 | Assess training needs of relevant public frontline workers such as the police/DOVVSU, social workers, and probation officers and relevant service providers
Activity 1.2.2 | Develop the training tools for the target institutions and pilot them
Activity 1.2.3 | Conduct training for the target group in the new policies in order to ensure effective implementation and enforcement
Activity 1.2.4 | Conduct training for the target group in the new policies in order to ensure effective implementation and enforcement
Activity 1.2.5 | Lobby government to mainstream child rights/protection courses in training curriculum of police officers, health workers, and other professionals
Activity 1.2.6 | Establish/strengthen child welfare structures such as the Local advisory Committee involving key child rights stakeholders at key communities in the Ashanti region
Activity 1.2.7 | Provide training on for LAC on their roles and responsibilities in accordance with the Ghanaian laws
Output 1.3 | Strengthened coordination and referral mechanisms for the protection of children at district levels | # of functional CP referral mechanisms existing in project areas | DCI semi-annual and annual reports | willingness of CBO to be available for training and apply knowledge gained
Output 1.3 |  | # of CBOs using knowledge gained on cp incident management and referral systems | DCI semi-annual and annual reports | willingness of CBO to be available for training and apply knowledge gained
Activity 1.3.1 | Identify gaps and weaknesses within case management mechanisms at formal and informal levels
Activity 1.3.2 | Develop/enrich Standard Operational procedures and case management guidelines for institutions that deal with cases of children and adapt them for use by community based structures
Activity 1.3.3 | Provide case management training for legal and social service institutions and community based structures that deal with cases of children
Activity 1.3.4 | Assist children case management CBOs and networks to sign an MoU with the Ministry of Gender, Children and Social Protection
Activity 1.3.5 | Facilitate regular meetings of the networks under the leadership of the Ministry of Gender and Children’s Welfare
Activity 1.3.6 | Conduct a survey to examine the existing practices between the formal child protection institutions and the traditional/informal community based structures
Activity 1.3.7 | Develop appropriate strategies to address the gaps and build better working relationship between the two levels of child protection based on findings of the survey
Activity 1.3.8 | Support the District Assembly and/or the Ministry of Gender and Children’s Welfare to develop district referral protocols on child abuse and Guidelines for the protection and treatment of children in conflict with the law
Activity 1.3.9 | Map out (and/or update) service providers for child victims of abuse and children in conflict with the law at district level and develop directory of services
Output 1.4 | Communities effectively supported to address underlying issues that influence vulnerability of children at the local level | % of children with birth registration documents | DCI semi-annual and annual reports, Departments of Births and Death Registry Reports | willingness of caregivers and communites to be available for training and apply knowledge gained
Output 1.4 |  | % of caregivers who are able to demonstrate understanding of CP | DCI semi-annual and annual reports, | willingness of caregivers and communites to be available for training and apply knowledge gained
Activity 1.4.1 | Organise community dialogue meetings involving all key players to discuss child rights issues and be able to prioritise and plan with their local resources in collaboration with the District Assembly and local child welfare structures
Activity 1.4.2 | Establish and/or strengthen child rights clubs and other young peoples group in schools and communities including using strategies that can promote wider participation, democracy and equal gender representation, equality and equity
Activity 1.4.3 | Train the clubs in child rights, advocacy/lobby skills and facilitate lobby/advocacy initiatives of young people geared towards improvement of their protection and welfare;
Activity 1.4.4 | Organise joint advocacy programmes with children/youths on child welfare issues
Activity 1.4.5 | Conduct a survey to understand the opportunities and challenges for micro-business development by poor people
Activity 1.4.6 | In collaboration with micro-finance institutions, local entrepreneurs and other members of the private sector, support poor families to be able to establish successful businesses that can take care of the welfare of their children
Outcome 2 | Enhanced gender equity and equality through the promotion of the rights of girls and young women | % of caregivers who are able to demonstrate understanding of CP | DCI Evaluation Report DCI Annual Monitoring Report | •Willingness of communities to work with issues of child right and engage duty bearers. •Availability of Funding for the project
Outcome 2 |  | % of children under 18 years who are married | DCI Evaluation Report DCI Annual Monitoring Report | •Willingness of communities to work with issues of child right and engage duty bearers. •Nationa policy on early marriage adopted and offenders prosecuted
Outcome 2 |  | % HHs approving for female genital mutilation/cutting (FGM/C) | DCI Evaluation Report DCI Annual Monitoring Report | •Willingness of communities to work with issues of child right and engage duty bearers. •Nationa policy on FGM adopted and offenders prosecuted
Outcome 2 |  | Prevalence of female genital mutilation/cutting (FGM/C) among women | DCI Evaluation Report DCI Annual Monitoring Report | •Willingness of communities to work with issues of child right and engage duty bearers. •Nationa policy on FGM adopted and offenders prosecuted
Outcome 2 |  | Prevalence of female genital mutilation/cutting (FGM/C) among girls | DCI Evaluation Report DCI Annual Monitoring Report | •Willingness of communities to work with issues of child right and engage duty bearers. •Nationa policy on FGM adopted and offenders prosecuted
Output 2.1 | To empower girls and young women with knowledge, skills and other resources required for their protection and overall development | # of functional girls clubs | DCI semi-annual and annual reports | Sustained support from caregivers and communities
Output 2.1 |  | % of girls knowledgeable in CP. | DCI semi-annual and annual reports | Sustained support from caregivers and communities
Activity 2.1.1 | Establish girls and young women’s groups in communities
Activity 2.1.2 | Support girls and young women’s groups to develop simple working documents that can guide their operations including membership drive and activities
Activity 2.1.3 | Provide training for girls and young women’s groups in GVB, gender equality and equity and right to participation and involvement in decision making and development at the local level
Activity 2.1.4 | Organise routine and regular life planning skills sessions for girls and young women
Activity 2.1.5 | Organise sessions with girls and young women on career development including giving them opportunity to meet with role models
Activity 2.1.6 | Facilitate the enrolment of girls and young women who are out of school into learning institutions in collaboration with Ministry of Education and other relevant agencies
Activity 2.1.7 | Facilitate the access of girls and womenin the informal sector to job through internships, apprenticeships and other means by the end of their trainings.
Activity 2.1.8 | Provide girls and young women in formal schools with necessary support that can ensure their retention and good output in school
Output 2.2 | Reduced harmful and negative cultural practices that affects the rights, protection and devlopment of girls and women | % of young women knowledgeable in CP. | DCI semi-annual and annual reports | Community willing and ready to adapt to behavioural change
Output 2.2 |  | # of researches undertaken to understand the root causes and negative cultural practices affecting protection and development of girls and women | DCI semi-annual and annual reports | Availability of funds to carry out research
Activity 2.2.1 | Conduct a survey on practices/laws/bi-laws that are harmful to the survival and development of girls and young women including documenting those that promote their protection and development
Activity 2.2.2 | Develop communication and awareness raising strategies against community based practices that are discriminatory and detrimental to girls and young women
Activity 2.2.3 | Organise community dialogue meetings and the production and displaying of IEC materials that can educate the local people about harmful practices and effect on girls, young women and the society in general
Activity 2.2.4 | Promote the inclusion of the special needs of girls and young women in the child protection system strengthening programme
Activity 2.2.5 | Lobby with community leaders to review discriminatory rules/bi-laws including those that promote gender based violence
Output 2.3 | Improved promotion and defence of the rights of girls through the influence of boys and girls | # of men reached in communuties on the promotion and rights of girls | DCI semi-annual and annual reports | Sustained support from communities and men groups in communities
Output 2.3 |  | # of boys reached in schools and communuties on the promotion and rights of girls | DCI Project reports (Annual & Semi-Annual), Club Registers, Club Report | Sustained support from caregivers and communities
Activity 2.3.1 | Identify influential boys and young men to serve as ambassadors and promoters of the rights of girls and young women in schools and communities
Activity 2.3.2 | Work with the boys and young men identified to develop strategies and develop plan on how they can be involved in exclusive girls rights projects
Activity 2.3.3 | Develop manuals or other tools and train staff and the ambassadors in how to involve boys and young men
Activity 2.3.4 | Support boys and girls groups to organise joint programmes that promote campaign for equity and equality, equal rights, equal participation, equal access and use of resources by boys and girls
Outcome 3 | Enhanced access to justice, rehabilitation and reintegration of children in conflict with the law and child victims of violence and economic exploitation | % of children aged between 12-18 knowledgeable in child protection and able to demonsrate right to survival,participation,education and protection | DCI Evaluation Report DCI Annual Monitoring Report | •Willingness of communities to work with issues of child right and engage duty bearers. •Availability of Funding for the project
Outcome 3 |  | % of children and caregivers who have utilized prevention or response interventions delivered or supported by DCI | DCI Evaluation Report DCI Annual Monitoring Report Most Significant Change Story | •Willingness of communities to work with issues of child right and engage duty bearers. •Availability of Funding for the project
Outcome 3 |  | % of men/married partners with improved attitudes towards domestic violence | DCI Evaluation Report DCI Annual Monitoring Report | •Willingness of communities to work with issues of child right and engage duty bearers. •Availability of Funding for the project
Output 3.1 | Generate public interest and collective response to child abuse particularly focusing on sexual abuse, neglect, child labour and child trafficking | % of communities with functional CP refereal systems | DCI semi-annual and annual reports | Willingness of communities to work with issues of child rights
Output 3.1 |  | # of HH reached with key messages in abuse, neglect, child labour and child trafficking | DCI semi-annual and annual reports | Willingness of communities to work with issues of child rights
Activity 3.1.1 | Conduct research to fully understand the trend and realities of child sexual abuse, neglect, labour and trafficking which keep showing as main child abuse issues in the Ashanti region
Activity 3.1.2 | Develop messages for awareness raising on the different kinds of child abuse prioritised by DCI-Ghana
Activity 3.1.3 | Disseminate the messages through radio, TV, posters, and other means of dissemination involving young people
Activity 3.1.4 | Develop tools that can be used for service delivery e.g counselling and legal advice
Activity 3.1.5 | Raise awareness of the public on child abuse and reporting channels and mechanisms including the role of DCI’s socio-legal defence centre in facilitating prosecution of cases of child abuse
Activity 3.1.6 | Provide legal advice and social support for victims and their families to be able to submit appropriate evidence to the police during the course of investigation
Activity 3.1.7 | Campaign for access to free medical examination and treatment for victims of sexual violence and other forms of gross abuses
Output 3.2 | Provide social support and legal defence for children in conflict with the law and child victims of violence/abuse | # of children supported through advocacy for their release from detension centers | DCI semi-annual and annual reports | Willingness of communities to work with issues of child rights
Output 3.2 |  | % of children aged between 12-18 knowledgeable in child protection and able to demonsrate right to survival,participation,education and protection | DCI semi-annual and annual reports | Willingness of communities to work with issues of child rights
Activity 3.2.1 | Develop minimum standards and guidelines for the operation of the socio-legal defence centre including its services, target group and cases that it deals with
Activity 3.2.2 | Develop a referral pathway for the centre including directory of services of other service providers;
Activity 3.2.3 | Provide legal advice, paralegal, psychosocial, mediation and family tracing and reunification training for social workers and other staff that manage cases of children at the socio-legal defence centre
Activity 3.2.4 | Pay regular visit to police stations, prisons and courts to identify children in detention
Activity 3.2.5 | Advocate for the release and/or diversion of cases of children held in police custody including mediation for pre-trial and non-judicial settlement of the matters
Output 3.3 | Ensure rehabilitation and reintegration of children in conflict with the law and child victims of abuse and/or economic exploitation | # of abused victims rehabilitated and integrated into communities and society | DCI semi-annual and annual reports | Willingness of communities to work with issues of child rights
Output 3.3 |  | # of government institutions/structures whose capacities has been built in rehabililation of abused victims | DCI semi-annual and annual reports | willingness of government institutions to be available for training and apply knowledge gained
Output 3.3 |  | # of CSOs & CBOs whose capacities have been built in rehabililation of abused victims | DCI semi-annual and annual reports | willingness of CBO to be available for training and apply knowledge gained
Activity 3.3.1 | Provide technical and logistics support to the DA and MGACW to develop guidelines on family tracing and reintegration of separated children
Activity 3.3.2 | Support the DA and MGACW to map out key partners including DCI-Gh that have experience and resource for family tracing and reintegration of separated children
Activity 3.3.3 | Support the DA and MGACW to sign MoU with all the partners identified and provide training for them on the new Guidelines on family tracing and reunification of the child
Activity 3.3.4 | Facilitate family reunification of children from police custody and prisons and other separated children at risk of coming in contact with the law as victim or offenders

## M&E Plan
Level | Summary of objectives | Indicator | Indicator Definition | Means of Verification | Data Collection methodology | Assumptions | Frequency of data collection
Programme Outcome (project goal) | Strenghtened child protection systems in Ghana to adequately prevent, respond to and manage child rights and protection issues. | % of children rights violation cases or issues as report by DOVSU | % of children rights violation cases or issues as report by DOVSU. This includes FGM, Forced and/orChild Marriage, sexual abuse etc | DCI Evaluation Report | • Official statistics (Data from DOVSU). • Evaluation • Documnetary Review | Stakeholders’ willingness to work with issues of child right. Availability of Funding for the project | Annually
Outcome 1 | Improved policy formulation and implementation by government including the district assemblies of Ghana aimed at filling child protection gaps | % of communities engaged in drafting and formulating CP policy | Proportion of communities that have been facilitated by DCI and other stakeholders in the drafting and formulation of CP related policies in Ghana. | DCI Evaluation Report DCI Annual Monitoring Report | • Official statistics (Data from DOVSU). • Evaluation • Documnetary Review | Stakeholders’ willingness to work with issues of child right. Functional in-coutry CSO coalitions Availability of Funding for the project | Annually
Outcome 1 |  | % of child protection policy, planning or practice changes that have been informed by evidence from civil society | Proportion of child policies, planning or practices changes that have been informed by evidence from civil society group activities including campaigns, events and lobbying etc. | DCI Evaluation Report DCI Annual Monitoring Report | • Official statistics (Data from DOVSU). • Evaluation • Documnetary Review | • Favourable cooperation of stakeholders on issue of children right •Functional in-coutry CSO coalitions •Availability of Funding for the project | Annually
Output 1.1 | Improved capacities of staff to lobby for and draft child protection policy that will guide the child protection system strengthening initiative in Ghana | # of staff who have capacity to undertake advocacy | Number of staff from DCI and other stakeholder organisation who have been trianed to do advocacy using context based approaches and skills such as media campaigns, lobbying service providers, public speaking, commissioning and publishing research, mass signature petitions, issueing of briefs etc. | DCI semi-annual and annual reports | Key Informant Interviews | •Willingness of communities to work with issues of child right and engage duty bearers. •Availability of Funding for the project | every six months
Output 1.1 |  | # of DCI staff trained in child protection system strengthening | Number of staff from DCI and other stakeholder organisation who have been trianed in Child rights, protection, preventaion and managemenge of abuse | DCI semi-annual and annual reports | Key Informant Interviews | •Availability of Funding for the project | every six months
Activity 1.1.1 | Conduct legislative reviews to identify gaps and evidences for law reforms
Activity 1.1.2 | Conduct legal research and examine the efficacy of the Ghana Children’s Act and other relevant laws
Activity 1.1.3 | Advocate for legal reforms with the view of harmonising laws with the new child protection policy
Activity 1.1.4 | Contribute to the drafting of the new bills and also lobby for the passage of the new bills into laws collaboration with UNICEF, GP CSC and other influential CSOs and coalitions
Activity 1.1.5 | Disseminate the new policies and laws particularly in local communities targeting both adults and children/youths, in collaboration with CBOs, journalists and other CSOs and relevant MDAs
Output 1.2 | Capacity of government institutions and relevant community based structures built in Child rights & protection Policies | # of community based organisations trained in incident management and referrals | Number of community based organisations who have been trianed by DCI on child protectiona and abuse incident management and referrals | DCI semi-annual and annual reports | Key Informant Interviews | willingness of CBO to be available for training and apply knowledge gained | every 6 months
Output 1.2 |  | # of government institutions/structures trained in Child rights & protection Policies | Number of government institutions/structures including district assemblies who have been trained in and can articulate issues around Child rights & protection Policies | DCI semi-annual and annual reports | Documentary review Key Informant Interviews | willingness of government institutions to be available for training and apply knowledge gained | every 6 months
Activity 1.2.1 | Assess training needs of relevant public frontline workers such as the police/DOVVSU, social workers, and probation officers and relevant service providers
Activity 1.2.2 | Develop the training tools for the target institutions and pilot them
Activity 1.2.3 | Conduct training for the target group in the new policies in order to ensure effective implementation and enforcement
Activity 1.2.4 | Conduct training for the target group in the new policies in order to ensure effective implementation and enforcement
Activity 1.2.5 | Lobby government to mainstream child rights/protection courses in training curriculum of police officers, health workers, and other professionals
Activity 1.2.6 | Establish/strengthen child welfare structures such as the Local advisory Committee involving key child rights stakeholders at key communities in the Ashanti region
Activity 1.2.7 | Provide training on for LAC on their roles and responsibilities in accordance with the Ghanaian laws
Output 1.3 | Strengthened coordination and referral mechanisms for the protection of children at district levels | # of functional CP referral mechanisms existing in project areas | Number of communities where HH members know the places/institutions in their communities or district where cases of child abuse and violation of rights are reported for redress | DCI semi-annual and annual reports | HH survey Key Informant Interviews | willingness of CBO to be available for training and apply knowledge gained | every 6 months
Output 1.3 |  | # of CBOs using knowledge gained on cp incident management and referral systems | Number of functional CBOs managing and referring CP incidents in communities. Functional CBO = CBO with executives/leadership, that meets regularly evidenced by minutes book and engages communities in trainings or sessions using context appropriate IEC materials | DCI semi-annual and annual reports | Documentary review Key Informant Interviews | willingness of CBO to be available for training and apply knowledge gained | every 6 months
Activity 1.3.1 | Identify gaps and weaknesses within case management mechanisms at formal and informal levels
Activity 1.3.2 | Develop/enrich Standard Operational procedures and case management guidelines for institutions that deal with cases of children and adapt them for use by community based structures
Activity 1.3.3 | Provide case management training for legal and social service institutions and community based structures that deal with cases of children
Activity 1.3.4 | Assist children case management CBOs and networks to sign an MoU with the Ministry of Gender, Children and Social Protection
Activity 1.3.5 | Facilitate regular meetings of the networks under the leadership of the Ministry of Gender and Children’s Welfare
Activity 1.3.6 | Conduct a survey to examine the existing practices between the formal child protection institutions and the traditional/informal community based structures
Activity 1.3.7 | Develop appropriate strategies to address the gaps and build better working relationship between the two levels of child protection based on findings of the survey
Activity 1.3.8 | Support the District Assembly and/or the Ministry of Gender and Children’s Welfare to develop district referral protocols on child abuse and Guidelines for the protection and treatment of children in conflict with the law
Activity 1.3.9 | Map out (and/or update) service providers for child victims of abuse and children in conflict with the law at district level and develop directory of services
Output 1.4 | Communities effectively supported to address underlying issues that influence vulnerability of children at the local level | % of children with birth registration documents | Proportion of children under age 18 whose births are reported registered | DCI semi-annual and annual reports, Departments of Births and Death Registry Reports | HH survey Documentary review | willingness of caregivers and communites to be available for training and apply knowledge gained | every 6 months
Output 1.4 |  | % of caregivers who are able to demonstrate understanding of CP | Proportion of children aged 12 - 18 who can mention at least 2 child's rights ( right to survival, participation, education and protection), 2 cases that be classified as child abuse cases, 2 instutions/mechanisms in place in their community or district where child right violation can be reported | DCI semi-annual and annual reports, | HH survey Key Informant Interviews | willingness of caregivers and communites to be available for training and apply knowledge gained | every 6 months
Activity 1.4.1 | Organise community dialogue meetings involving all key players to discuss child rights issues and be able to prioritise and plan with their local resources in collaboration with the District Assembly and local child welfare structures
Activity 1.4.2 | Establish and/or strengthen child rights clubs and other young peoples group in schools and communities including using strategies that can promote wider participation, democracy and equal gender representation, equality and equity
Activity 1.4.3 | Train the clubs in child rights, advocacy/lobby skills and facilitate lobby/advocacy initiatives of young people geared towards improvement of their protection and welfare;
Activity 1.4.4 | Organise joint advocacy programmes with children/youths on child welfare issues
Activity 1.4.5 | Conduct a survey to understand the opportunities and challenges for micro-business development by poor people
Activity 1.4.6 | In collaboration with micro-finance institutions, local entrepreneurs and other members of the private sector, support poor families to be able to establish successful businesses that can take care of the welfare of their children
Outcome 2 | Enhanced gender equity and equality through the promotion of the rights of girls and young women | % of caregivers who are able to demonstrate understanding of CP | Proportion of children aged 12 - 18 who can mention at least 2 child's rights ( right to survival, participation, education and protection), 2 cases that be classified as child abuse cases, 2 instutions/mechanisms in place in their community or district where child right violation can be reported | DCI Evaluation Report DCI Annual Monitoring Report | • Official statistics (Data from DOVSU). • Evaluation • Annual HH Monitoring Survey | •Willingness of communities to work with issues of child right and engage duty bearers. •Availability of Funding for the project | Annually
Outcome 2 |  | % of children under 18 years who are married | Proportion of girls age under 18 years who were first married or in union before the age of 18 | DCI Evaluation Report DCI Annual Monitoring Report | • Official statistics (Data from DOVSU). • Evaluation • Documnetary Review | •Willingness of communities to work with issues of child right and engage duty bearers. •Nationa policy on early marriage adopted and offenders prosecuted | Annually
Outcome 2 |  | % HHs approving for female genital mutilation/cutting (FGM/C) | Proporting of HH where the father/mother 15-49 years favour the continuation of female genital mutilation/ cutting (FGM/C) | DCI Evaluation Report DCI Annual Monitoring Report | • Official statistics (Data from DOVSU). • Evaluation • Documnetary Review | •Willingness of communities to work with issues of child right and engage duty bearers. •Nationa policy on FGM adopted and offenders prosecuted | Annually
Outcome 2 |  | Prevalence of female genital mutilation/cutting (FGM/C) among women | Proportion of women age 15-49 years who report to have undergone any form of female genital mutilation/cutting (FGM/C) | DCI Evaluation Report DCI Annual Monitoring Report | • Official statistics (Data from DOVSU). • Evaluation • Documnetary Review | •Willingness of communities to work with issues of child right and engage duty bearers. •Nationa policy on FGM adopted and offenders prosecuted | Annually
Outcome 2 |  | Prevalence of female genital mutilation/cutting (FGM/C) among girls | Proportion of girls age 0-14 years who have undergone any form of female genital mutilation/ cutting (FGM/C), as reported by mothers | DCI Evaluation Report DCI Annual Monitoring Report | • Official statistics (Data from DOVSU). • Evaluation • Documnetary Review | •Willingness of communities to work with issues of child right and engage duty bearers. •Nationa policy on FGM adopted and offenders prosecuted | Annually
Output 2.1 | To empower girls and young women with knowledge, skills and other resources required for their protection and overall development | # of functional girls clubs | Functional Children/girls = clubs with a executive/leadership, has a patron, meet regularly evidenced by minutes or attendance book | DCI semi-annual and annual reports | • Annual HH Monitoring Survey • Key Informant Interviews | Sustained support from caregivers and communities | every 6 months
Output 2.1 |  | % of girls knowledgeable in CP. | Proportion of girls 12-18 can mention at least 2 child's rights (right to survival, participation, education and protection), 2 cases that be classified as child abuse cases, 2 instutions/mechanisms in place in their community or district where child right violation can be reported | DCI semi-annual and annual reports | • Annual HH Monitoring Survey • Key Informant Interviews | Sustained support from caregivers and communities | every 6 months
Activity 2.1.1 | Establish girls and young women’s groups in communities
Activity 2.1.2 | Support girls and young women’s groups to develop simple working documents that can guide their operations including membership drive and activities
Activity 2.1.3 | Provide training for girls and young women’s groups in GVB, gender equality and equity and right to participation and involvement in decision making and development at the local level
Activity 2.1.4 | Organise routine and regular life planning skills sessions for girls and young women
Activity 2.1.5 | Organise sessions with girls and young women on career development including giving them opportunity to meet with role models
Activity 2.1.6 | Facilitate the enrolment of girls and young women who are out of school into learning institutions in collaboration with Ministry of Education and other relevant agencies
Activity 2.1.7 | Facilitate the access of girls and womenin the informal sector to job through internships, apprenticeships and other means by the end of their trainings.
Activity 2.1.8 | Provide girls and young women in formal schools with necessary support that can ensure their retention and good output in school
Output 2.2 | Reduced harmful and negative cultural practices that affects the rights, protection and devlopment of girls and women | % of young women knowledgeable in CP. | Proportion of young women can mention at least 2 child's rights ( right to survival, participation, education and protection), 2 cases that be classified as child abuse cases, 2 instutions/mechanisms in place in their community or district where child right violation can be reported | DCI semi-annual and annual reports | • Annual HH Monitoring Survey | Community willing and ready to adapt to behavioural change | every 6 months
Output 2.2 |  | # of researches undertaken to understand the root causes and negative cultural practices affecting protection and development of girls and women | Number of researches undertaken to understand the root causes and negative cultural practices affecting the protection and devlopment of girls and women in communities | DCI semi-annual and annual reports | • Annual HH Monitoring Survey | Availability of funds to carry out research | every 6 months
Activity 2.2.1 | Conduct a survey on practices/laws/bi-laws that are harmful to the survival and development of girls and young women including documenting those that promote their protection and development
Activity 2.2.2 | Develop communication and awareness raising strategies against community based practices that are discriminatory and detrimental to girls and young women
Activity 2.2.3 | Organise community dialogue meetings and the production and displaying of IEC materials that can educate the local people about harmful practices and effect on girls, young women and the society in general
Activity 2.2.4 | Promote the inclusion of the special needs of girls and young women in the child protection system strengthening programme
Activity 2.2.5 | Lobby with community leaders to review discriminatory rules/bi-laws including those that promote gender based violence
Output 2.3 | Improved promotion and defence of the rights of girls through the influence of boys and girls | # of men reached in communuties on the promotion and rights of girls | Proportion of men can mention at least 2 child's rights (right to survival, participation, education and protection), 2 cases that be classified as child abuse cases, 2 instutions/mechanisms in place in their community or district where child right violation can be reported. | DCI semi-annual and annual reports | • HH Monitoring Survey | Sustained support from communities and men groups in communities | every 6 months
Output 2.3 |  | # of boys reached in schools and communuties on the promotion and rights of girls | Proportion of boys 12-18 can mention at least 2 child's rights (right to survival, participation, education and protection), 2 cases that be classified as child abuse cases, 2 instutions/mechanisms in place in their community or district where child right violation can be reported. | DCI Project reports (Annual & Semi-Annual), Club Registers, Club Report | • HH Monitoring Survey | Sustained support from caregivers and communities | every 6 months
Activity 2.3.1 | Identify influential boys and young men to serve as ambassadors and promoters of the rights of girls and young women in schools and communities
Activity 2.3.2 | Work with the boys and young men identified to develop strategies and develop plan on how they can be involved in exclusive girls rights projects
Activity 2.3.3 | Develop manuals or other tools and train staff and the ambassadors in how to involve boys and young men
Activity 2.3.4 | Support boys and girls groups to organise joint programmes that promote campaign for equity and equality, equal rights, equal participation, equal access and use of resources by boys and girls
Outcome 3 | Enhanced access to justice, rehabilitation and reintegration of children in conflict with the law and child victims of violence and economic exploitation | % of children aged between 12-18 knowledgeable in child protection and able to demonsrate right to survival,participation,education and protection | proportion of children aged between 12-18 knowledgeable in child protection and able to demonsrate right to survival,participation,education and protection | DCI Evaluation Report DCI Annual Monitoring Report | • Official statistics (Data from DOVSU). • Evaluation • Documnetary Review • Most Significant Change Stories | •Willingness of communities to work with issues of child right and engage duty bearers. •Availability of Funding for the project | Annually
Outcome 3 |  | % of children and caregivers who have utilized prevention or response interventions delivered or supported by DCI | Proportion of children and caregivers in a 12-month period who have utilized prevention or response interventions delivered or supported by DCI | DCI Evaluation Report DCI Annual Monitoring Report Most Significant Change Story | • Official statistics (Data from DOVSU). • Evaluation • Documnetary Review • Most Significant Change Stories | •Willingness of communities to work with issues of child right and engage duty bearers. •Availability of Funding for the project | Annually
Outcome 3 |  | % of men/married partners with improved attitudes towards domestic violence | Number of women who state that a husband/partner is justified in hitting or beating his wife in at least one of the following circumstances: (1) she goes out without telling him, (2) she neglects the children, (3) she argues with him, (4) she refuses sex with him, (5) she burns the food | DCI Evaluation Report DCI Annual Monitoring Report | • Official statistics (Data from DOVSU). • Evaluation • Documnetary Review • Most Significant Change Stories | •Willingness of communities to work with issues of child right and engage duty bearers. •Availability of Funding for the project | Annually
Output 3.1 | Generate public interest and collective response to child abuse particularly focusing on sexual abuse, neglect, child labour and child trafficking | % of communities with functional CP refereal systems | Proportion of communities where there exist centers, institutions or people who undertake the following ; 1. Receive reports on abuse or violation of the rights of community members especially children and women 2. Counsel with, handle and manage those who are abused or have their right violated especially 3. Take action on offenders by seeking redress for victims through laid down structures. | DCI semi-annual and annual reports | • Annual HH Monitoring Survey • Key Informant Interviews | Willingness of communities to work with issues of child rights | every 6 months
Output 3.1 |  | # of HH reached with key messages in abuse, neglect, child labour and child trafficking | Number of HH reached with key messages in abuse, neglect, child labour and child trafficking through the use of context appropriate IEC materials | DCI semi-annual and annual reports | • HH Monitoring Survey | Willingness of communities to work with issues of child rights | every 6 months
Activity 3.1.1 | Conduct research to fully understand the trend and realities of child sexual abuse, neglect, labour and trafficking which keep showing as main child abuse issues in the Ashanti region
Activity 3.1.2 | Develop messages for awareness raising on the different kinds of child abuse prioritised by DCI-Ghana
Activity 3.1.3 | Disseminate the messages through radio, TV, posters, and other means of dissemination involving young people
Activity 3.1.4 | Develop tools that can be used for service delivery e.g counselling and legal advice
Activity 3.1.5 | Raise awareness of the public on child abuse and reporting channels and mechanisms including the role of DCI’s socio-legal defence centre in facilitating prosecution of cases of child abuse
Activity 3.1.6 | Provide legal advice and social support for victims and their families to be able to submit appropriate evidence to the police during the course of investigation
Activity 3.1.7 | Campaign for access to free medical examination and treatment for victims of sexual violence and other forms of gross abuses
Output 3.2 | Provide social support and legal defence for children in conflict with the law and child victims of violence/abuse | # of children supported through advocacy for their release from detension centers | number of children supported through advocacy for their release from detension centers such as prisons, police station and sometimes courts as result of their involvement in child protection violattion issues | DCI semi-annual and annual reports | • HH Monitoring Survey | Willingness of communities to work with issues of child rights | every 6 months
Output 3.2 |  | % of children aged between 12-18 knowledgeable in child protection and able to demonsrate right to survival,participation,education and protection | Proportion of girls 12-18 can mention at least 2 child's rights (right to survival, participation, education and protection), 2 cases that be classified as child abuse cases, 2 instutions/mechanisms in place in their community or district where child right violation can be reported | DCI semi-annual and annual reports | • HH Monitoring Survey | Willingness of communities to work with issues of child rights | Annually
Activity 3.2.1 | Develop minimum standards and guidelines for the operation of the socio-legal defence centre including its services, target group and cases that it deals with
Activity 3.2.2 | Develop a referral pathway for the centre including directory of services of other service providers;
Activity 3.2.3 | Provide legal advice, paralegal, psychosocial, mediation and family tracing and reunification training for social workers and other staff that manage cases of children at the socio-legal defence centre
Activity 3.2.4 | Pay regular visit to police stations, prisons and courts to identify children in detention
Activity 3.2.5 | Advocate for the release and/or diversion of cases of children held in police custody including mediation for pre-trial and non-judicial settlement of the matters
Output 3.3 | Ensure rehabilitation and reintegration of children in conflict with the law and child victims of abuse and/or economic exploitation | # of abused victims rehabilitated and integrated into communities and society | number of abused victims rehabilitated and integrated into communities and society | DCI semi-annual and annual reports | • Annual HH Monitoring Survey • Key Informant Interviews | Willingness of communities to work with issues of child rights | every 6 months
Output 3.3 |  | # of government institutions/structures whose capacities has been built in rehabililation of abused victims | Number of government institutions/structures who have been trained on couselling and manangement/ handlingskills, rehabililation and integration of abused victims. | DCI semi-annual and annual reports | • Annual HH Monitoring Survey • Key Informant Interviews | willingness of government institutions to be available for training and apply knowledge gained | every 6 months
Output 3.3 |  | # of CSOs & CBOs whose capacities have been built in rehabililation of abused victims | Number of Civil Society Organisations (CSOs) and Community Based Organisations (CBOs) who have been trained on couselling and manangement/ handlingskills, rehabililation and integration of abused victims. | DCI semi-annual and annual reports | • Annual HH Monitoring Survey • Key Informant Interviews | willingness of CBO to be available for training and apply knowledge gained | every 6 months
Activity 3.3.1 | Provide technical and logistics support to the DA and MGACW to develop guidelines on family tracing and reintegration of separated children
Activity 3.3.2 | Support the DA and MGACW to map out key partners including DCI-Gh that have experience and resource for family tracing and reintegration of separated children
Activity 3.3.3 | Support the DA and MGACW to sign MoU with all the partners identified and provide training for them on the new Guidelines on family tracing and reunification of the child
Activity 3.3.4 | Facilitate family reunification of children from police custody and prisons and other separated children at risk of coming in contact with the law as victim or offenders

## Indicator Performance Tracker
Level of Objective | Indicators | Baseline | YEAR 1 | [7 empty] | YEAR 2 | [7 empty] | YEAR 3 Life of Project (3 Year) Result | [7 empty] | Life of Project (3 Year) Results
|  |  | 6 month target | 6-month Achieved | 12 month target | 12 month Achieved | Total Target | Total Achievement | % Achievement | % Variance | 6 month target | 6-month Achieved | 12 month target | 12 month Achieved | Total Target | Total Achievement | % Achievement | % Variance | 6 month target | 6-month Achieved | 12 month target | 12 month Achieved | Total Target | Total Achievement | % Achievement | % Variance | Life of Project Target | Life of Project Achieved | Life of Project Achievement (%) | Explanation of Target Variances (for -/+ 10% achieved or under achieved results)
Programme Outcome (project goal) | % of children rights violation cases or issues as report by DOVSU | 18% | 3 | 1 | 3 | 4 | 6 | 5 | 83.3333 | 16.6667 | 5 | 3 | 4 | 2 | 9 | 5 | 55.5556 | 44.4444 | 5 | 3 | 4 | 2 | 9 | 5 | 55.5556 | 44.4444 | 23 | 15 | 65.22% | The project could not achieve because of funding was cut at the beginning of the implementation year due to donors reducing their support
Outcome 1 | % of communities engaged in drafting and formulating CP policy | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Outcome 1 | % of child protection policy, planning or practice changes that have been informed by evidence from civil society | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 1.1 | # of staff who have capacity to undertake advocacy | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 1.1 | # of DCI staff trained in child protection system strengthening | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 1.2 | # of community based organisations trained in incident management and referrals | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 1.2 | # of government institutions/structures trained in Child rights & protection Policies | [5 empty] | 0 | 0
Output 1.3 | # of functional CP referral mechanisms existing in project areas | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 1.3 | # of CBOs using knowledge gained on cp incident management and referral systems | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 1.4 | % of children with birth registration documents | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 1.4 | % of caregivers who are able to demonstrate understanding of CP | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Outcome 2 | % of caregivers who are able to demonstrate understanding of CP | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Outcome 2 | % of children under 18 years who are married | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Outcome 2 | % HHs approving for female genital mutilation/cutting (FGM/C) | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Outcome 2 | Prevalence of female genital mutilation/cutting (FGM/C) among women | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Outcome 2 | Prevalence of female genital mutilation/cutting (FGM/C) among girls | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 2.1 | # of functional girls clubs | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 2.1 | % of girls knowledgeable in CP. | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 2.2 | % of young women knowledgeable in CP. | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 2.2 | # of researches undertaken to understand the root causes and negative cultural practices affecting protection and development of girls and women | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 2.3 | # of men reached in communuties on the promotion and rights of girls | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 2.3 | # of boys reached in schools and communuties on the promotion and rights of girls | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Outcome 3 | % of children aged between 12-18 knowledgeable in child protection and able to demonsrate right to survival,participation,education and protection | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Outcome 3 | % of children and caregivers who have utilized prevention or response interventions delivered or supported by DCI | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Outcome 3 | % of men/married partners with improved attitudes towards domestic violence | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 3.1 | % of communities with functional CP refereal systems | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 3.1 | # of HH reached with key messages in abuse, neglect, child labour and child trafficking | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 3.2 | # of children supported through advocacy for their release from detension centers | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 3.2 | % of children aged between 12-18 knowledgeable in child protection and able to demonsrate right to survival,participation,education and protection | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 3.3 | # of abused victims rehabilitated and integrated into communities and society | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 3.3 | # of government institutions/structures whose capacities has been built in rehabililation of abused victims | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
Output 3.3 | # of CSOs & CBOs whose capacities have been built in rehabililation of abused victims | [5 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0%
[27 empty] | 0 |  | 0

## Activity Implementation Plan-1
Level of Objective | Summary of Objectives | Description Of Activity | January | February | March | April | May | June | July | August | September | October | November | December | Annual | Person responsible | External Partner/ Supplier
Programme Outcome (project goal) | Strenghtened child protection systems in Ghana to adequately prevent, respond to and manage child rights and protection issues.
Outcome 1 | Improved policy formulation and implementation by government including the district assemblies of Ghana aimed at filling child protection gaps | [13 empty] | 0
Output 1.1 | Improved capacities of staff to lobby for and draft child protection policy that will guide the child protection system strengthening initiative in Ghana | [13 empty] | 0
Activity 1.1.1 | Conduct legislative reviews to identify gaps and evidences for law reforms | # times legislatives were done | [12 empty] | 0
Activity 1.1.2 | Conduct legal research and examine the efficacy of the Ghana Children’s Act and other relevant laws | # of researches conducted | 1 | [5 empty] | 1 |  |  |  | 1 |  | 3
Activity 1.1.3 | Advocate for legal reforms with the view of harmonising laws with the new child protection policy | # of advocacy meetings conducted |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 2
Activity 1.1.4 | Contribute to the drafting of the new bills and also lobby for the passage of the new bills into laws collaboration with UNICEF, GP CSC and other influential CSOs and coalitions | [13 empty] | 0
Activity 1.1.5 | Disseminate the new policies and laws particularly in local communities targeting both adults and children/youths, in collaboration with CBOs, journalists and other CSOs and relevant MDAs | [13 empty] | 0
Output 1.2 | Capacity of government institutions and relevant community based structures built in Child rights & protection Policies | [13 empty] | 0
Activity 1.2.1 | Assess training needs of relevant public frontline workers such as the police/DOVVSU, social workers, and probation officers and relevant service providers | [13 empty] | 0
Activity 1.2.2 | Develop the training tools for the target institutions and pilot them | [13 empty] | 0
Activity 1.2.3 | Conduct training for the target group in the new policies in order to ensure effective implementation and enforcement | [13 empty] | 0
Activity 1.2.4 | Conduct training for the target group in the new policies in order to ensure effective implementation and enforcement | [13 empty] | 0
Activity 1.2.5 | Lobby government to mainstream child rights/protection courses in training curriculum of police officers, health workers, and other professionals | [13 empty] | 0
Activity 1.2.6 | Establish/strengthen child welfare structures such as the Local advisory Committee involving key child rights stakeholders at key communities in the Ashanti region | [13 empty] | 0
Activity 1.2.7 | Provide training on for LAC on their roles and responsibilities in accordance with the Ghanaian laws | [13 empty] | 0
Output 1.3 | Strengthened coordination and referral mechanisms for the protection of children at district levels | [13 empty] | 0
Activity 1.3.1 | Identify gaps and weaknesses within case management mechanisms at formal and informal levels | [13 empty] | 0
Activity 1.3.2 | Develop/enrich Standard Operational procedures and case management guidelines for institutions that deal with cases of children and adapt them for use by community based structures | [13 empty] | 0
Activity 1.3.3 | Provide case management training for legal and social service institutions and community based structures that deal with cases of children | [13 empty] | 0
Activity 1.3.4 | Assist children case management CBOs and networks to sign an MoU with the Ministry of Gender, Children and Social Protection | [13 empty] | 0
Activity 1.3.5 | Facilitate regular meetings of the networks under the leadership of the Ministry of Gender and Children’s Welfare | [13 empty] | 0
Activity 1.3.6 | Conduct a survey to examine the existing practices between the formal child protection institutions and the traditional/informal community based structures | [13 empty] | 0
Activity 1.3.7 | Develop appropriate strategies to address the gaps and build better working relationship between the two levels of child protection based on findings of the survey | [13 empty] | 0
Activity 1.3.8 | Support the District Assembly and/or the Ministry of Gender and Children’s Welfare to develop district referral protocols on child abuse and Guidelines for the protection and treatment of children in conflict with the law | [13 empty] | 0
Activity 1.3.9 | Map out (and/or update) service providers for child victims of abuse and children in conflict with the law at district level and develop directory of services | [13 empty] | 0
Output 1.4 | Communities effectively supported to address underlying issues that influence vulnerability of children at the local level | [13 empty] | 0
Activity 1.4.1 | Organise community dialogue meetings involving all key players to discuss child rights issues and be able to prioritise and plan with their local resources in collaboration with the District Assembly and local child welfare structures | [13 empty] | 0
Activity 1.4.2 | Establish and/or strengthen child rights clubs and other young peoples group in schools and communities including using strategies that can promote wider participation, democracy and equal gender representation, equality and equity | [13 empty] | 0
Activity 1.4.3 | Train the clubs in child rights, advocacy/lobby skills and facilitate lobby/advocacy initiatives of young people geared towards improvement of their protection and welfare; | [13 empty] | 0
Activity 1.4.4 | Organise joint advocacy programmes with children/youths on child welfare issues | [13 empty] | 0
Activity 1.4.5 | Conduct a survey to understand the opportunities and challenges for micro-business development by poor people | [13 empty] | 0
Activity 1.4.6 | In collaboration with micro-finance institutions, local entrepreneurs and other members of the private sector, support poor families to be able to establish successful businesses that can take care of the welfare of their children | [13 empty] | 0
Outcome 2 | Enhanced gender equity and equality through the promotion of the rights of girls and young women | [13 empty] | 0
Output 2.1 | To empower girls and young women with knowledge, skills and other resources required for their protection and overall development | [13 empty] | 0
Activity 2.1.1 | Establish girls and young women’s groups in communities | [13 empty] | 0
Activity 2.1.2 | Support girls and young women’s groups to develop simple working documents that can guide their operations including membership drive and activities | [13 empty] | 0
Activity 2.1.3 | Provide training for girls and young women’s groups in GVB, gender equality and equity and right to participation and involvement in decision making and development at the local level | [13 empty] | 0
Activity 2.1.4 | Organise routine and regular life planning skills sessions for girls and young women | [13 empty] | 0
Activity 2.1.5 | Organise sessions with girls and young women on career development including giving them opportunity to meet with role models | [13 empty] | 0
Activity 2.1.6 | Facilitate the enrolment of girls and young women who are out of school into learning institutions in collaboration with Ministry of Education and other relevant agencies | [13 empty] | 0
Activity 2.1.7 | Facilitate the access of girls and womenin the informal sector to job through internships, apprenticeships and other means by the end of their trainings. | [13 empty] | 0
Activity 2.1.8 | Provide girls and young women in formal schools with necessary support that can ensure their retention and good output in school | [13 empty] | 0
Output 2.2 | Reduced harmful and negative cultural practices that affects the rights, protection and devlopment of girls and women | [13 empty] | 0
Activity 2.2.1 | Conduct a survey on practices/laws/bi-laws that are harmful to the survival and development of girls and young women including documenting those that promote their protection and development | [13 empty] | 0
Activity 2.2.2 | Develop communication and awareness raising strategies against community based practices that are discriminatory and detrimental to girls and young women | [13 empty] | 0
Activity 2.2.3 | Organise community dialogue meetings and the production and displaying of IEC materials that can educate the local people about harmful practices and effect on girls, young women and the society in general | [13 empty] | 0
Activity 2.2.4 | Promote the inclusion of the special needs of girls and young women in the child protection system strengthening programme | [13 empty] | 0
Activity 2.2.5 | Lobby with community leaders to review discriminatory rules/bi-laws including those that promote gender based violence | [13 empty] | 0
Output 2.3 | Improved promotion and defence of the rights of girls through the influence of boys and girls | [13 empty] | 0
Activity 2.3.1 | Identify influential boys and young men to serve as ambassadors and promoters of the rights of girls and young women in schools and communities | [13 empty] | 0
Activity 2.3.2 | Work with the boys and young men identified to develop strategies and develop plan on how they can be involved in exclusive girls rights projects | [13 empty] | 0
Activity 2.3.3 | Develop manuals or other tools and train staff and the ambassadors in how to involve boys and young men | [13 empty] | 0
Activity 2.3.4 | Support boys and girls groups to organise joint programmes that promote campaign for equity and equality, equal rights, equal participation, equal access and use of resources by boys and girls | [13 empty] | 0
Outcome 3 | Enhanced access to justice, rehabilitation and reintegration of children in conflict with the law and child victims of violence and economic exploitation | [13 empty] | 0
Output 3.1 | Generate public interest and collective response to child abuse particularly focusing on sexual abuse, neglect, child labour and child trafficking | [13 empty] | 0
Activity 3.1.1 | Conduct research to fully understand the trend and realities of child sexual abuse, neglect, labour and trafficking which keep showing as main child abuse issues in the Ashanti region | [13 empty] | 0
Activity 3.1.2 | Develop messages for awareness raising on the different kinds of child abuse prioritised by DCI-Ghana | [13 empty] | 0
Activity 3.1.3 | Disseminate the messages through radio, TV, posters, and other means of dissemination involving young people | [13 empty] | 0
Activity 3.1.4 | Develop tools that can be used for service delivery e.g counselling and legal advice | [13 empty] | 0
Activity 3.1.5 | Raise awareness of the public on child abuse and reporting channels and mechanisms including the role of DCI’s socio-legal defence centre in facilitating prosecution of cases of child abuse | [13 empty] | 0
Activity 3.1.6 | Provide legal advice and social support for victims and their families to be able to submit appropriate evidence to the police during the course of investigation | [13 empty] | 0
Activity 3.1.7 | Campaign for access to free medical examination and treatment for victims of sexual violence and other forms of gross abuses | [13 empty] | 0
Output 3.2 | Provide social support and legal defence for children in conflict with the law and child victims of violence/abuse | [13 empty] | 0
Activity 3.2.1 | Develop minimum standards and guidelines for the operation of the socio-legal defence centre including its services, target group and cases that it deals with | [13 empty] | 0
Activity 3.2.2 | Develop a referral pathway for the centre including directory of services of other service providers; | [13 empty] | 0
Activity 3.2.3 | Provide legal advice, paralegal, psychosocial, mediation and family tracing and reunification training for social workers and other staff that manage cases of children at the socio-legal defence centre | [13 empty] | 0
Activity 3.2.4 | Pay regular visit to police stations, prisons and courts to identify children in detention | [13 empty] | 0
Activity 3.2.5 | Advocate for the release and/or diversion of cases of children held in police custody including mediation for pre-trial and non-judicial settlement of the matters | [13 empty] | 0
Output 3.3 | Ensure rehabilitation and reintegration of children in conflict with the law and child victims of abuse and/or economic exploitation | [13 empty] | 0
Activity 3.3.1 | Provide technical and logistics support to the DA and MGACW to develop guidelines on family tracing and reintegration of separated children | [13 empty] | 0
Activity 3.3.2 | Support the DA and MGACW to map out key partners including DCI-Gh that have experience and resource for family tracing and reintegration of separated children | [13 empty] | 0
Activity 3.3.3 | Support the DA and MGACW to sign MoU with all the partners identified and provide training for them on the new Guidelines on family tracing and reunification of the child | [13 empty] | 0
Activity 3.3.4 | Facilitate family reunification of children from police custody and prisons and other separated children at risk of coming in contact with the law as victim or offenders | [13 empty] | 0

## Activity Implementation Plan-2
Level of Objective | Summary of Objectives | Description Of Activity | January | February | March | April | May | June | July | August | September | October | November | December | Annual | Person responsible | External Partner/ Supplier
Programme Outcome (project goal) | Strenghtened child protection systems in Ghana to adequately prevent, respond to and manage child rights and protection issues.
Outcome 1 | Improved policy formulation and implementation by government including the district assemblies of Ghana aimed at filling child protection gaps | [13 empty] | 0
Output 1.1 | Improved capacities of staff to lobby for and draft child protection policy that will guide the child protection system strengthening initiative in Ghana | [13 empty] | 0
Activity 1.1.1 | Conduct legislative reviews to identify gaps and evidences for law reforms | # times legislatives were done | [12 empty] | 0
Activity 1.1.2 | Conduct legal research and examine the efficacy of the Ghana Children’s Act and other relevant laws | # of researches conducted | 1 | [5 empty] | 1 |  |  |  | 1 |  | 3
Activity 1.1.3 | Advocate for legal reforms with the view of harmonising laws with the new child protection policy | # of advocacy meetings conducted |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 2
Activity 1.1.4 | Contribute to the drafting of the new bills and also lobby for the passage of the new bills into laws collaboration with UNICEF, GP CSC and other influential CSOs and coalitions | [13 empty] | 0
Activity 1.1.5 | Disseminate the new policies and laws particularly in local communities targeting both adults and children/youths, in collaboration with CBOs, journalists and other CSOs and relevant MDAs | [13 empty] | 0
Output 1.2 | Capacity of government institutions and relevant community based structures built in Child rights & protection Policies | [13 empty] | 0
Activity 1.2.1 | Assess training needs of relevant public frontline workers such as the police/DOVVSU, social workers, and probation officers and relevant service providers | [13 empty] | 0
Activity 1.2.2 | Develop the training tools for the target institutions and pilot them | [13 empty] | 0
Activity 1.2.3 | Conduct training for the target group in the new policies in order to ensure effective implementation and enforcement | [13 empty] | 0
Activity 1.2.4 | Conduct training for the target group in the new policies in order to ensure effective implementation and enforcement | [13 empty] | 0
Activity 1.2.5 | Lobby government to mainstream child rights/protection courses in training curriculum of police officers, health workers, and other professionals | [13 empty] | 0
Activity 1.2.6 | Establish/strengthen child welfare structures such as the Local advisory Committee involving key child rights stakeholders at key communities in the Ashanti region | [13 empty] | 0
Activity 1.2.7 | Provide training on for LAC on their roles and responsibilities in accordance with the Ghanaian laws | [13 empty] | 0
Output 1.3 | Strengthened coordination and referral mechanisms for the protection of children at district levels | [13 empty] | 0
Activity 1.3.1 | Identify gaps and weaknesses within case management mechanisms at formal and informal levels | [13 empty] | 0
Activity 1.3.2 | Develop/enrich Standard Operational procedures and case management guidelines for institutions that deal with cases of children and adapt them for use by community based structures | [13 empty] | 0
Activity 1.3.3 | Provide case management training for legal and social service institutions and community based structures that deal with cases of children | [13 empty] | 0
Activity 1.3.4 | Assist children case management CBOs and networks to sign an MoU with the Ministry of Gender, Children and Social Protection | [13 empty] | 0
Activity 1.3.5 | Facilitate regular meetings of the networks under the leadership of the Ministry of Gender and Children’s Welfare | [13 empty] | 0
Activity 1.3.6 | Conduct a survey to examine the existing practices between the formal child protection institutions and the traditional/informal community based structures | [13 empty] | 0
Activity 1.3.7 | Develop appropriate strategies to address the gaps and build better working relationship between the two levels of child protection based on findings of the survey | [13 empty] | 0
Activity 1.3.8 | Support the District Assembly and/or the Ministry of Gender and Children’s Welfare to develop district referral protocols on child abuse and Guidelines for the protection and treatment of children in conflict with the law | [13 empty] | 0
Activity 1.3.9 | Map out (and/or update) service providers for child victims of abuse and children in conflict with the law at district level and develop directory of services | [13 empty] | 0
Output 1.4 | Communities effectively supported to address underlying issues that influence vulnerability of children at the local level | [13 empty] | 0
Activity 1.4.1 | Organise community dialogue meetings involving all key players to discuss child rights issues and be able to prioritise and plan with their local resources in collaboration with the District Assembly and local child welfare structures | [13 empty] | 0
Activity 1.4.2 | Establish and/or strengthen child rights clubs and other young peoples group in schools and communities including using strategies that can promote wider participation, democracy and equal gender representation, equality and equity | [13 empty] | 0
Activity 1.4.3 | Train the clubs in child rights, advocacy/lobby skills and facilitate lobby/advocacy initiatives of young people geared towards improvement of their protection and welfare; | [13 empty] | 0
Activity 1.4.4 | Organise joint advocacy programmes with children/youths on child welfare issues | [13 empty] | 0
Activity 1.4.5 | Conduct a survey to understand the opportunities and challenges for micro-business development by poor people | [13 empty] | 0
Activity 1.4.6 | In collaboration with micro-finance institutions, local entrepreneurs and other members of the private sector, support poor families to be able to establish successful businesses that can take care of the welfare of their children | [13 empty] | 0
Outcome 2 | Enhanced gender equity and equality through the promotion of the rights of girls and young women | [13 empty] | 0
Output 2.1 | To empower girls and young women with knowledge, skills and other resources required for their protection and overall development | [13 empty] | 0
Activity 2.1.1 | Establish girls and young women’s groups in communities | [13 empty] | 0
Activity 2.1.2 | Support girls and young women’s groups to develop simple working documents that can guide their operations including membership drive and activities | [13 empty] | 0
Activity 2.1.3 | Provide training for girls and young women’s groups in GVB, gender equality and equity and right to participation and involvement in decision making and development at the local level | [13 empty] | 0
Activity 2.1.4 | Organise routine and regular life planning skills sessions for girls and young women | [13 empty] | 0
Activity 2.1.5 | Organise sessions with girls and young women on career development including giving them opportunity to meet with role models | [13 empty] | 0
Activity 2.1.6 | Facilitate the enrolment of girls and young women who are out of school into learning institutions in collaboration with Ministry of Education and other relevant agencies | [13 empty] | 0
Activity 2.1.7 | Facilitate the access of girls and womenin the informal sector to job through internships, apprenticeships and other means by the end of their trainings. | [13 empty] | 0
Activity 2.1.8 | Provide girls and young women in formal schools with necessary support that can ensure their retention and good output in school | [13 empty] | 0
Output 2.2 | Reduced harmful and negative cultural practices that affects the rights, protection and devlopment of girls and women | [13 empty] | 0
Activity 2.2.1 | Conduct a survey on practices/laws/bi-laws that are harmful to the survival and development of girls and young women including documenting those that promote their protection and development | [13 empty] | 0
Activity 2.2.2 | Develop communication and awareness raising strategies against community based practices that are discriminatory and detrimental to girls and young women | [13 empty] | 0
Activity 2.2.3 | Organise community dialogue meetings and the production and displaying of IEC materials that can educate the local people about harmful practices and effect on girls, young women and the society in general | [13 empty] | 0
Activity 2.2.4 | Promote the inclusion of the special needs of girls and young women in the child protection system strengthening programme | [13 empty] | 0
Activity 2.2.5 | Lobby with community leaders to review discriminatory rules/bi-laws including those that promote gender based violence | [13 empty] | 0
Output 2.3 | Improved promotion and defence of the rights of girls through the influence of boys and girls | [13 empty] | 0
Activity 2.3.1 | Identify influential boys and young men to serve as ambassadors and promoters of the rights of girls and young women in schools and communities | [13 empty] | 0
Activity 2.3.2 | Work with the boys and young men identified to develop strategies and develop plan on how they can be involved in exclusive girls rights projects | [13 empty] | 0
Activity 2.3.3 | Develop manuals or other tools and train staff and the ambassadors in how to involve boys and young men | [13 empty] | 0
Activity 2.3.4 | Support boys and girls groups to organise joint programmes that promote campaign for equity and equality, equal rights, equal participation, equal access and use of resources by boys and girls | [13 empty] | 0
Outcome 3 | Enhanced access to justice, rehabilitation and reintegration of children in conflict with the law and child victims of violence and economic exploitation | [13 empty] | 0
Output 3.1 | Generate public interest and collective response to child abuse particularly focusing on sexual abuse, neglect, child labour and child trafficking | [13 empty] | 0
Activity 3.1.1 | Conduct research to fully understand the trend and realities of child sexual abuse, neglect, labour and trafficking which keep showing as main child abuse issues in the Ashanti region | [13 empty] | 0
Activity 3.1.2 | Develop messages for awareness raising on the different kinds of child abuse prioritised by DCI-Ghana | [13 empty] | 0
Activity 3.1.3 | Disseminate the messages through radio, TV, posters, and other means of dissemination involving young people | [13 empty] | 0
Activity 3.1.4 | Develop tools that can be used for service delivery e.g counselling and legal advice | [13 empty] | 0
Activity 3.1.5 | Raise awareness of the public on child abuse and reporting channels and mechanisms including the role of DCI’s socio-legal defence centre in facilitating prosecution of cases of child abuse | [13 empty] | 0
Activity 3.1.6 | Provide legal advice and social support for victims and their families to be able to submit appropriate evidence to the police during the course of investigation | [13 empty] | 0
Activity 3.1.7 | Campaign for access to free medical examination and treatment for victims of sexual violence and other forms of gross abuses | [13 empty] | 0
Output 3.2 | Provide social support and legal defence for children in conflict with the law and child victims of violence/abuse | [13 empty] | 0
Activity 3.2.1 | Develop minimum standards and guidelines for the operation of the socio-legal defence centre including its services, target group and cases that it deals with | [13 empty] | 0
Activity 3.2.2 | Develop a referral pathway for the centre including directory of services of other service providers; | [13 empty] | 0
Activity 3.2.3 | Provide legal advice, paralegal, psychosocial, mediation and family tracing and reunification training for social workers and other staff that manage cases of children at the socio-legal defence centre | [13 empty] | 0
Activity 3.2.4 | Pay regular visit to police stations, prisons and courts to identify children in detention | [13 empty] | 0
Activity 3.2.5 | Advocate for the release and/or diversion of cases of children held in police custody including mediation for pre-trial and non-judicial settlement of the matters | [13 empty] | 0
Output 3.3 | Ensure rehabilitation and reintegration of children in conflict with the law and child victims of abuse and/or economic exploitation | [13 empty] | 0
Activity 3.3.1 | Provide technical and logistics support to the DA and MGACW to develop guidelines on family tracing and reintegration of separated children | [13 empty] | 0
Activity 3.3.2 | Support the DA and MGACW to map out key partners including DCI-Gh that have experience and resource for family tracing and reintegration of separated children | [13 empty] | 0
Activity 3.3.3 | Support the DA and MGACW to sign MoU with all the partners identified and provide training for them on the new Guidelines on family tracing and reunification of the child | [13 empty] | 0
Activity 3.3.4 | Facilitate family reunification of children from police custody and prisons and other separated children at risk of coming in contact with the law as victim or offenders | [13 empty] | 0

## Activity Implementation Plan-3
Level of Objective | Summary of Objectives | Description Of Activity | January | February | March | April | May | June | July | August | September | October | November | December | Annual | Person responsible | External Partner/ Supplier
Programme Outcome (project goal) | Strenghtened child protection systems in Ghana to adequately prevent, respond to and manage child rights and protection issues.
Outcome 1 | Improved policy formulation and implementation by government including the district assemblies of Ghana aimed at filling child protection gaps
Output 1.1 | Improved capacities of staff to lobby for and draft child protection policy that will guide the child protection system strengthening initiative in Ghana
Activity 1.1.1 | Conduct legislative reviews to identify gaps and evidences for law reforms | # times legislatives were done | [12 empty] | 0
Activity 1.1.2 | Conduct legal research and examine the efficacy of the Ghana Children’s Act and other relevant laws | # of researches conducted | 1 | [5 empty] | 1 |  |  |  | 1 |  | 3
Activity 1.1.3 | Advocate for legal reforms with the view of harmonising laws with the new child protection policy | # of advocacy meetings conducted |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 2
Activity 1.1.4 | Contribute to the drafting of the new bills and also lobby for the passage of the new bills into laws collaboration with UNICEF, GP CSC and other influential CSOs and coalitions | [13 empty] | 0
Activity 1.1.5 | Disseminate the new policies and laws particularly in local communities targeting both adults and children/youths, in collaboration with CBOs, journalists and other CSOs and relevant MDAs | [13 empty] | 0
Output 1.2 | Capacity of government institutions and relevant community based structures built in Child rights & protection Policies | [13 empty] | 0
Activity 1.2.1 | Assess training needs of relevant public frontline workers such as the police/DOVVSU, social workers, and probation officers and relevant service providers | [13 empty] | 0
Activity 1.2.2 | Develop the training tools for the target institutions and pilot them | [13 empty] | 0
Activity 1.2.3 | Conduct training for the target group in the new policies in order to ensure effective implementation and enforcement | [13 empty] | 0
Activity 1.2.4 | Conduct training for the target group in the new policies in order to ensure effective implementation and enforcement | [13 empty] | 0
Activity 1.2.5 | Lobby government to mainstream child rights/protection courses in training curriculum of police officers, health workers, and other professionals | [13 empty] | 0
Activity 1.2.6 | Establish/strengthen child welfare structures such as the Local advisory Committee involving key child rights stakeholders at key communities in the Ashanti region | [13 empty] | 0
Activity 1.2.7 | Provide training on for LAC on their roles and responsibilities in accordance with the Ghanaian laws | [13 empty] | 0
Output 1.3 | Strengthened coordination and referral mechanisms for the protection of children at district levels
Activity 1.3.1 | Identify gaps and weaknesses within case management mechanisms at formal and informal levels | [13 empty] | 0
Activity 1.3.2 | Develop/enrich Standard Operational procedures and case management guidelines for institutions that deal with cases of children and adapt them for use by community based structures | [13 empty] | 0
Activity 1.3.3 | Provide case management training for legal and social service institutions and community based structures that deal with cases of children | [13 empty] | 0
Activity 1.3.4 | Assist children case management CBOs and networks to sign an MoU with the Ministry of Gender, Children and Social Protection | [13 empty] | 0
Activity 1.3.5 | Facilitate regular meetings of the networks under the leadership of the Ministry of Gender and Children’s Welfare | [13 empty] | 0
Activity 1.3.6 | Conduct a survey to examine the existing practices between the formal child protection institutions and the traditional/informal community based structures | [13 empty] | 0
Activity 1.3.7 | Develop appropriate strategies to address the gaps and build better working relationship between the two levels of child protection based on findings of the survey | [13 empty] | 0
Activity 1.3.8 | Support the District Assembly and/or the Ministry of Gender and Children’s Welfare to develop district referral protocols on child abuse and Guidelines for the protection and treatment of children in conflict with the law | [13 empty] | 0
Activity 1.3.9 | Map out (and/or update) service providers for child victims of abuse and children in conflict with the law at district level and develop directory of services | [13 empty] | 0
Output 1.4 | Communities effectively supported to address underlying issues that influence vulnerability of children at the local level
Activity 1.4.1 | Organise community dialogue meetings involving all key players to discuss child rights issues and be able to prioritise and plan with their local resources in collaboration with the District Assembly and local child welfare structures | [13 empty] | 0
Activity 1.4.2 | Establish and/or strengthen child rights clubs and other young peoples group in schools and communities including using strategies that can promote wider participation, democracy and equal gender representation, equality and equity | [13 empty] | 0
Activity 1.4.3 | Train the clubs in child rights, advocacy/lobby skills and facilitate lobby/advocacy initiatives of young people geared towards improvement of their protection and welfare; | [13 empty] | 0
Activity 1.4.4 | Organise joint advocacy programmes with children/youths on child welfare issues | [13 empty] | 0
Activity 1.4.5 | Conduct a survey to understand the opportunities and challenges for micro-business development by poor people | [13 empty] | 0
Activity 1.4.6 | In collaboration with micro-finance institutions, local entrepreneurs and other members of the private sector, support poor families to be able to establish successful businesses that can take care of the welfare of their children | [13 empty] | 0
Outcome 2 | Enhanced gender equity and equality through the promotion of the rights of girls and young women
Output 2.1 | To empower girls and young women with knowledge, skills and other resources required for their protection and overall development
Activity 2.1.1 | Establish girls and young women’s groups in communities | [13 empty] | 0
Activity 2.1.2 | Support girls and young women’s groups to develop simple working documents that can guide their operations including membership drive and activities | [13 empty] | 0
Activity 2.1.3 | Provide training for girls and young women’s groups in GVB, gender equality and equity and right to participation and involvement in decision making and development at the local level | [13 empty] | 0
Activity 2.1.4 | Organise routine and regular life planning skills sessions for girls and young women | [13 empty] | 0
Activity 2.1.5 | Organise sessions with girls and young women on career development including giving them opportunity to meet with role models | [13 empty] | 0
Activity 2.1.6 | Facilitate the enrolment of girls and young women who are out of school into learning institutions in collaboration with Ministry of Education and other relevant agencies | [13 empty] | 0
Activity 2.1.7 | Facilitate the access of girls and womenin the informal sector to job through internships, apprenticeships and other means by the end of their trainings. | [13 empty] | 0
Activity 2.1.8 | Provide girls and young women in formal schools with necessary support that can ensure their retention and good output in school | [13 empty] | 0
Output 2.2 | Reduced harmful and negative cultural practices that affects the rights, protection and devlopment of girls and women
Activity 2.2.1 | Conduct a survey on practices/laws/bi-laws that are harmful to the survival and development of girls and young women including documenting those that promote their protection and development | [13 empty] | 0
Activity 2.2.2 | Develop communication and awareness raising strategies against community based practices that are discriminatory and detrimental to girls and young women | [13 empty] | 0
Activity 2.2.3 | Organise community dialogue meetings and the production and displaying of IEC materials that can educate the local people about harmful practices and effect on girls, young women and the society in general | [13 empty] | 0
Activity 2.2.4 | Promote the inclusion of the special needs of girls and young women in the child protection system strengthening programme | [13 empty] | 0
Activity 2.2.5 | Lobby with community leaders to review discriminatory rules/bi-laws including those that promote gender based violence | [13 empty] | 0
Output 2.3 | Improved promotion and defence of the rights of girls through the influence of boys and girls
Activity 2.3.1 | Identify influential boys and young men to serve as ambassadors and promoters of the rights of girls and young women in schools and communities | [13 empty] | 0
Activity 2.3.2 | Work with the boys and young men identified to develop strategies and develop plan on how they can be involved in exclusive girls rights projects | [13 empty] | 0
Activity 2.3.3 | Develop manuals or other tools and train staff and the ambassadors in how to involve boys and young men | [13 empty] | 0
Activity 2.3.4 | Support boys and girls groups to organise joint programmes that promote campaign for equity and equality, equal rights, equal participation, equal access and use of resources by boys and girls | [13 empty] | 0
Outcome 3 | Enhanced access to justice, rehabilitation and reintegration of children in conflict with the law and child victims of violence and economic exploitation
Output 3.1 | Generate public interest and collective response to child abuse particularly focusing on sexual abuse, neglect, child labour and child trafficking
Activity 3.1.1 | Conduct research to fully understand the trend and realities of child sexual abuse, neglect, labour and trafficking which keep showing as main child abuse issues in the Ashanti region | [13 empty] | 0
Activity 3.1.2 | Develop messages for awareness raising on the different kinds of child abuse prioritised by DCI-Ghana | [13 empty] | 0
Activity 3.1.3 | Disseminate the messages through radio, TV, posters, and other means of dissemination involving young people | [13 empty] | 0
Activity 3.1.4 | Develop tools that can be used for service delivery e.g counselling and legal advice | [13 empty] | 0
Activity 3.1.5 | Raise awareness of the public on child abuse and reporting channels and mechanisms including the role of DCI’s socio-legal defence centre in facilitating prosecution of cases of child abuse | [13 empty] | 0
Activity 3.1.6 | Provide legal advice and social support for victims and their families to be able to submit appropriate evidence to the police during the course of investigation | [13 empty] | 0
Activity 3.1.7 | Campaign for access to free medical examination and treatment for victims of sexual violence and other forms of gross abuses | [13 empty] | 0
Output 3.2 | Provide social support and legal defence for children in conflict with the law and child victims of violence/abuse
Activity 3.2.1 | Develop minimum standards and guidelines for the operation of the socio-legal defence centre including its services, target group and cases that it deals with | [13 empty] | 0
Activity 3.2.2 | Develop a referral pathway for the centre including directory of services of other service providers; | [13 empty] | 0
Activity 3.2.3 | Provide legal advice, paralegal, psychosocial, mediation and family tracing and reunification training for social workers and other staff that manage cases of children at the socio-legal defence centre | [13 empty] | 0
Activity 3.2.4 | Pay regular visit to police stations, prisons and courts to identify children in detention | [13 empty] | 0
Activity 3.2.5 | Advocate for the release and/or diversion of cases of children held in police custody including mediation for pre-trial and non-judicial settlement of the matters | [13 empty] | 0
Output 3.3 | Ensure rehabilitation and reintegration of children in conflict with the law and child victims of abuse and/or economic exploitation
Activity 3.3.1 | Provide technical and logistics support to the DA and MGACW to develop guidelines on family tracing and reintegration of separated children | [13 empty] | 0
Activity 3.3.2 | Support the DA and MGACW to map out key partners including DCI-Gh that have experience and resource for family tracing and reintegration of separated children | [13 empty] | 0
Activity 3.3.3 | Support the DA and MGACW to sign MoU with all the partners identified and provide training for them on the new Guidelines on family tracing and reunification of the child | [13 empty] | 0
Activity 3.3.4 | Facilitate family reunification of children from police custody and prisons and other separated children at risk of coming in contact with the law as victim or offenders | [13 empty] | 0