M&E STRATEGY (FRAMEWORK)

FOR

DCI-GHANA SECTION

March 2016

Authored by:

P.O. Box CT 7334, Cantonments, Accra

Loc: No. 6 Ahinakwa Street, Adabraka – Odorna, Accra

Contact: 02431722035 / 0243408123/0261644441

E-mail:Tcdi@gmail.com / esselv1011@gmail.com

Contents

i.	ACKNOWLEDGEMENT	3

ii.	AFFIRMATION	3

iii.	LIST OF ACRONYMS	4

1.0	BACKGROUND OF DEFENCE FOR CHILDREN INTERNATIONAL (DCI) GHANA.	5

1.1 AIM OF DCI	5

1.2 OBJECTIVES	5

1.3 VISION	6

1.4 MISSION	6

1.5 VALUES	6

2.0 Brief Overview of the Monitoring and Evaluation Strategy	6

2.1 PURPOSE OF THE MONITORING & EVALUATION STRATEGY	6

2.2 RESULTS FRAMEWORK	7

2.2.1 DCI Results Framework	7

2.2.2 Relationship of the DCI Results Framework to Ghana Development Objectives	10

2.2.3 Key Assumptions Underlying the Project Results Framework	11

3. PERFORMANCE MANAGEMENT COMPONENTS AND PROCESSES	11

3.1 PERFORMANCE MONITORING PLAN (PMP)	11

3.1.1 Data Acquisition/Collection Plan	11

3.1.2Method and Approaches of data collection	12

3.1.3 Data Capture, Storage and Analysis	12

3.1.4 Data Quality Control and Assessments	13

3.1.5 Project Baseline, Evaluation and Special Studies	14

Evaluation	14

3.2 Knowledge Management and Learning Plan	15

3.2.1 Communication	15

3.2.2 Reporting	16

4.0 Role and Responsibilities of the M&E Specialist	17

4.1 Role of  M&E Officer	18

# ACKNOWLEDGEMENT

The Consultant (TDCL Group) wishes to express its appreciation to DCI for their immense support in this exercise. Special thanks go to the M&E Specialist &Officerfor their reviews and inputs, preparation of the Terms of Reference (TOR).

# AFFIRMATION

Except as acknowledged by the references in this report to other authors and publications, the document described herein consists of a joint work of the consultant (TDCL group), as part of the requirements of DCI. Information must be used only with their consent.

PRINCIPAL AUTHOR:

Victor Essel

Benjamin AsareYeboah

Richard Okai

March, 2016.

# LIST OF ACRONYMS

| DCI | Defence for Children International |
| --- | --- |
| ECOSOC |  |
| M&E | Monitoring and Evaluation |
| PMP | Performance Monitoring Plan |
| UNCRC |  |
| USAID |  |

# BACKGROUND OF DEFENCE FOR CHILDREN INTERNATIONAL (DCI) GHANA.

Defence for Children International is an independent non-governmental organization and a global movement for children’s rights. It has been promoting and protecting children’s rights on a global, regional, national and local level for over 30 years. Defence for Children International is represented through its national sections and associated members in 47 countries worldwide, with an International Secretariat based in Geneva, Switzerland. DCI was one of the drafters of the UNCRC and has a consultative status with the UN ECOSOC.

Defence for Children International Ghana is the national section of DCI in Ghana. It became a DCI section in 1997 during the International General Assembly of DCI held in Dakar. It is officially registered and active in Ghana since 1996. DCI-Ghana’s head office is currently in Kumasi with a branch office in Obuasi. Defence for Children Ghana operates in Ghana for and with children carrying out initiatives for the protection and promotion of rights in the following areas:

- Juvenile Justice

- Child Protection with specific programmes on girls and young women

- Sexual Gender Based Violence and other forms of child abuse

- Child Labour and Child Trafficking

## 1.1 AIM OF DCI

To promote and protect the rights of children as enshrined in the UN Convention on the rights of the child and the Ghanaian laws that concern children.

## 1.2 OBJECTIVES

- To influence the development, enforcement and implementation of policies that protect the rights of children

- To foster sustainable cooperation and solidarity with government, UN and other agencies on children’s rights

- To sensitise the public on the rights of the child

- To highlight child rights violations at national and international level in order to promote accountability and access to justice for the victims

- To facilitate the rehabilitation and reintegration of children from prisons, child victims of abuse and other vulnerable children

## 1.3 VISION

A Ghana where children’s rights are fully known and respected by all

## 1.4 MISSION

DCI Ghana operates to defend the rights of the child by advocating for and disseminating policies that protect the rights of children, building the capacities of child protection institutions and structures at national, district and community levels as well as empowering children for their self-protection and overall development.

## 1.5 VALUES

- We are professional

- We are sensitive to child rights issues

- We treat all child related cases with confidentiality and equality

- We are concerned with the welfare and protection of all children

# 2.0 Brief Overview of the Monitoring and Evaluation Strategy

DCI M&E strategy follows the guidance of EU commission and USAID ADS 203 M&E guidance. The document serves as the project’s Monitoring and Evaluation Plan (M&E Plan). The M&E Plan is a tool for planning, managing, evaluating, and documenting progress towards achieving the goals of the project. It will methodologically enable the evaluation of DCI project’s relevance, effectiveness, efficiency, impact and sustainability. It will be part the overarching learning plan that is based on adaptive management, sound science for management, stakeholder participation, and periodic self-evaluation. The M&E Strategy includes two major components. The Performance Monitoring Plan (PMP) and its associated indicator reporting which is tied to DCI strategy aim and intermediate results is the first part with the knowledge management and learning strategy to communicate and share information, results, and lessons—and solicit input and feedback for adaptive management the second aspect of the strategy.

The first section of the M&E Strategy is the PMP, which presents the overarching results framework (Figure 1), indicators, targets, and plan for data quality assurance. It describes the process for developing rapid assessments and baselines, which will be the basis for subsequent routine monitoring, periodic assessments and subsequent learning and adaptive management. The PMP lays out a calendar of performance management tasks, describes how data is collected and how the project will assess the limitations and quality of data. Thereafter follows the plan for knowledge management and learning.

## 2.1PURPOSE OF THE MONITORING & EVALUATION STRATEGY

The M&E strategy is designed to help track progress on all Project implementation in relation to its stated goal and Intermediate Results. As a living document, it will be used internally for routine monitoring, learning, and adaptive management and externally as a tool to engage stakeholders in analyzing and understanding data—and using it to inform management questions and decisions. It will also ensure accountability to donors and all stakeholders.

## 2.2 RESULTS FRAMEWORK

### 2.2.1 DCI Results Framework

The Results Framework is shown in Figure 1. It depicts the expected levels of change that DCI seeks to achieve in implementing it projects. This includes a positively reworded goal of;Child protection system in Ghana is adequately strengthened and able to prevent and respond to child abuse. The potential beneficial population of DCI projects is estimated to be over 130,000 people directly and up to two million indirectly.

DCI integrated results framework include three intermediate result (IR) areas to achieve the project goal:

- IR 1: Influence policy formulation and implementation by the government including the district assemblies of Ghana aimed at filling child protection gaps

- IR 2: Enhanced gender equity and equality through the promotion of the rights of girls and young women

- IR 3: Enhanced access to justice, rehabilitation and reintegration of children in conflict with the law and child victims of violence and economic exploitation

Figure 1. Graphical Representation of Results Framework

### 2.2.2 Relationship of the DCI Results Framework to Ghana Development Objectives

The DCI results framework and associated indicators conform and contribute to the National Medium Term Development Framework (NMTDPF) Policy Objectives that are relevant to the Ministry of Gender, Children and Social Protection.

These are as follows:

- Promote effective child development in all communities, especially deprived areas

- Protect children against violence, abuse and exploitation

- Ensure a more effective appreciation of and inclusion of disability issues in national discourse

- Promote gender equity in political, social and economic development systems and outcomes

- Enhance institutional arrangement for inter and intra sectorial collaboration.

- Safeguard the security, safety and protection of the rights of the vulnerable in society, especially the girl child and women.

DCI results framework also aligns to UN convention on the right of the Child which addresses principles of non-discrimination; adherence to the best interests of the child; the right to life, survival and development; and the right to participate. They represent the underlying requirements for any and all rights to be realized.

Survival and development rights : These are rights to the resources, skills and contributions necessary for the survival and full development of the child. They include rights to adequate food, shelter, clean water, formal education, primary health care, leisure and recreation, cultural activities and information about their rights. These rights require not only the existence of the means to fulfil the rights but also access to them. Specific articles address the needs of child refugees, children with disabilities and children of minority or indigenous groups.

Protection rights : These rights include protection from all forms of child abuse, neglect, exploitation and cruelty, including the right to special protection in times of war and protection from abuse in the criminal justice system.

Participation rights: Children are entitled to the freedom to express opinions and to have a say in matters affecting their social, economic, religious, cultural and political life. Participation rights include the right to express opinions and be heard, the right to information and freedom of association.  Engaging these rights as they mature helps children bring about the realization of all their rights and prepares them for an active role in society.

The equality and interconnection of rights are stressed in the Convention. In addition to governments’ obligations, children and parents are responsible for respecting the rights of others—particularly each other. Children’s understanding of rights will vary depending on age and parents in particular should tailor the issues they discuss, the way in which they answer questions and discipline methods to the age and maturity of the individual child.

The results framework includes several important cross-cutting themes including capacity development of key government and civil society organizations, social learning, gender mainstreaming and Public-Private-Partnerships. The PMP has mainstreamed indicators that capture progress towards these cross-cutting themes.

### 2.2.3 Key Assumptions Underlying the Project Results Framework

This framework makes critical assumptions about possible external factors which are likely to be used on DCI projects which otherwise may affect ability to make measurable improvements in achieving the goal of DCI. This includes:

- The Government of Ghana (GOG) provides political support to implement policy changes needed.

- Stakeholders’ willingness to work with issues of child right.

- Favorable cooperation from the parents of the victims and the victims themselves

- Functional government systems and structures

# 3. PERFORMANCE MANAGEMENT COMPONENTS AND PROCESSES

This section of the DCI  M&E strategy describes the performance monitoring system and provides a description of program’s data acquisition/collection plan for the various levels of indicators (Impact, outcome and output),data capture, storage and analysis, Communication and reporting, Data Quality control and Assessments and Surveys (Project Baseline, Evaluation and Special studies)

## 3.1 PERFORMANCE MONITORING PLAN (PMP)

### 3.1.1 Data Acquisition/Collection Plan

Program indicators are presented to measure the effect of DCI interventions that seeks to improve and strength systems and structure with the operational areas. Some of the indicators and targets measured through the Project are simple and straight forward (e.g. number of community based organizations knowledgeable in incident management and referrals, Number of children engaging in decision making). For these indicators project deliverables will be measured using pre and post test data sources and evidence that the targets have been met. Other indicators and targets that are more complex will use mix methods for data collection during surveys.

### 3.1.2Method and Approaches of Data Collection

The data for many objectives and outcome indicators will be drawn from surveys/assessments conducted by DCI in conjunction with Implementing partners and service providers whiles the lower-level indicators will be drawn from the project records.

The following methods and tools are used to track and monitor performance:

- Data collection is standardized by developing forms and checklists for the implementing partners and field staff to apply. This will include sharing the PMP and indicator reference sheets to ensure that the indicators are well understood.

- All DCI projects will have designated M&E staff support who is trained in indicator definitions, data collection and reporting systems.

- Spatial data and GIS will be used for reporting—collecting primary data sets and geo-referencing all locations (including activity locations and zones of influence) where implementation will occur.

- A secure information management and activity project database will help track the development, implementation, and impact of activities.

### 3.1.3 Data Capture, Storage and Analysis

The M&E unit of DCI will use wide range of methods for capturing, analyzing and storing performance data and information generated in the course of the implementation of the Ghana DCI. The DCI will use research methods from the social sciences as well as participatory methods. Where necessary, the M&E will adapt an existing method or design an entirely new method that will enable the DCI team to collect comprehensive data for reporting purposes.

DCI will use the following methods in data gathering:

- Quantitative methods

- Qualitative methods

Quantitative Data Capture Methods

Based on the indicators, asset of data collection tools have been designed to measure quantitative data for reporting and decision making purposes. In instances where quantitative data is required on some indicators, the census method will be used. The following quantitative data collection strategies would thus be used:

- Observing and recording/counting the number of participants at capacity-building sessions;

- DCI  PMP designed excel template will be used to report on quarterly performance indicators to obtain secondary data

- Household surveys of impact indicators with measures will also be employed

Qualitative Data Capture Methods

DCI will employ the use of qualitative data capture methods to gather in-depth understanding of human behavior and the reasons that govern such behavior. The qualitative methods will assist DCI to investigate the why and how behind certain situations, decision, actions and behavior of the community people, children and other actors during the course of the implementation of Projects. For instance, if a certain proportion of the population sees child rights abuses as normal, DCI can employ qualitative methods to understand reasons behind such quantitative data. The following qualitative methods would be used:

- Focus group discussions

- Key informant interviews

- Informal interviews using checklist to triangulate information obtained from field officers regarding outcomes of the project intervention.

- Most Significant Change story collection

- Use of photo and GIS mapping documentation.

The M&E Unit will establish and maintain a Robust monitoring system, using Microsoft Excel or other database software to store and manage PMP parameters by the project from routine field monitoring exercise. Analyzed data will be disaggregated based on project component, districts, age and gender. Results of the analysis will be illustrated visually with tables, charts, and diagrams, as often as possible. Field officers will also be required to do simple data synthesis and use the results in writing field reports. Data from surveys/assessments will be analyzed using statistical software (SPSS/Epi Info)

DCI and its Implementing Partners will be given basic data analysis training, including GIS, to enable them transform the field data into tables, charts, and other diagrams for reporting purposes.

### 3.1.4 Data Quality Control and Assessments

Data quality standards that will be adhered to will include the following:

- Validity: Data should clearly and adequately represent the intended result. It should also be clear whether the data reflect a bias.

- Integrity: Data that are collected, analyzed, and reported should have established mechanisms in place to reduce the possibility that they are intentionally manipulated for political or personal reasons.

- Precision: Data should be sufficiently precise to present a fair picture of performance and enable management decision-making at the appropriate levels.

- Reliability: Data should reflect stable and consistent data collection processes and analysis methods from over time.

# Timeliness: Data should be timely enough to influence management decision-making at the appropriate levels.

DCI will work to assure that all indicator data is properly collected, analyzed and stored. Projects will be capacitated to use mobile data collection platform to conduct baseline surveys and other monitoring operations. If mobile data collection platforms are feasible, they would significantly enhance data quality and timeliness. DCI will develop appropriate information security protocols to ensure that information stored in the database is secure as well as protocols for staff access to the information. DCI will develop Data Quality Assessment Checklists which will be used to assess the Quality of Data implementing partners submit to the project.

The M&E officer will conduct data verification through site visits and select one indicator (or more) on which the partner has reported and check the partner’s understanding of the indicator, data collection methodology, reporting chain and supporting documentation

# The Monitoring, Evaluation and Learning officer/Specialist will also be responsible for training all implementing partners on how to enter data accurately and in a timely fashion and ensure proper evidence is also collected. The M&E officer/specialist will also undertake Data quality control and assurance checks via field visits and phone interviews with project beneficiaries.

### 3.1.5 Project Baseline, Evaluation and Special Studies

Establishment of Baselines

In order to assess the status of progress over the strategic year of DCI and phases of all DCI projects, DCI will conduct baselines within the first year of every project inception. This will enable DCI projects to understand how the changes are linked (or not) to project interventions. Projects will conduct baselines and mid/end of project follow up assessments using a quasi-experimental design that looks at pre-post project and non-project control sites, or more specifically difference in differences time series designs that estimate the difference between the pre-post, within-subjects differences of treatment and control groups. Where possible, secondary data would be obtained and analysed to form the baseline indicators for project monitoring and assessments. Project will use this methodological design where appropriate and practical and considering cost constraints to assess impacts.

## Evaluation

Evaluation will be conducted at the end the phases or DCI strategy end year to assess impact of projects intervention. This will be done with the full participation of all the stakeholders.  A local external consultant and a DCI M & E staff will lead the evaluation process.

Measuring Gender Impact

Gender equity is a cross cutting theme and will be assessed during Baselines and Evaluations. This will enable DCI to understand how the project’s activities impact girls, boys, and the dynamics between them. This will include collecting gender disaggregated data whenever appropriate on impact, outcome and output indicators.

## 3.2 Knowledge Management and Learning Plan

## 3.2.1 Communication

DCI projects will be designed to facilitate learning and information exchange through face to face meetings and access to virtual information. This will create a well of information that includes past repertoire of project and others as well as new information generated by the project and partners are available for planning and decision making. DCI knowledge management system will be used internally to code and track information, people, and contacts—working as a tool for PMP indicator reporting and to maximize transparency. It will also be a go-to site for information and knowledge sharing.

DCI will utilize variety of tools and approaches to ensure that key communications messages are disseminated in a ‘user-friendly’ manner that responds to the specific circumstances of targeted audiences and stakeholder groups at community, district, national and international levels. DCI will use and strengthen the robust networks and continuous contacts developed.

The Project will maintain participatory and transparent knowledge management flow that is integrated throughout the implementation of the project. This means that under each IR there will be targeted communication interventions aimed at 1) working with relevant stakeholders to inform, assess and plan for upcoming activities on an iterative basis; 2) updating relevant stakeholders on activity progress including key challenges and successes; and 3) sharing activity outcomes and lessons learned with relevant stakeholders. Project knowledge management and communications will therefore be continuous and will be meant to inform Project stakeholders about project progress and outcomes, as well as to guide upcoming project activities and implementation. The DCI will use a two-tiered knowledge management and communications approach:

The first tier knowledge management is corporate and internal, and involves clarifying for implementing partners protocols for branding and documentation; the need for timely and regular progress reports and success stories in the form of work plans, annual reports, technical reports, and factsheets, weekly FtF bulletins and most significant change stories. DCI will maintain an interactive and comprehensive website, but also work to provide steady feeds of information to donors and ensure partners and regional stakeholder groups are posting accurate, up-to-the-minute information on events, findings and developments.

The second tier of DCI communications is a series of carefully coordinated national and regional Policy Campaigns on emerging technical and scientific information and policy dialogues that are timed to match ongoing decision processes. Messages will be sure to capture stakeholder concerns including those of women and children who are typically overlooked. The campaigns will include early actions and Legislative Reform, a special communications plan focusing on reducing child protection and others listed in the technical application.

Specific communication tools and activities that will be used to support the policy campaigns and share knowledge and lessons generated by the DCI include:

- Translating key policy and legislative briefs, scientific findings and other lessons learned from the project into vernacular language (targeting community based audiences);

- Developing visual communications through pamphlets, story-boards, bill boards and posters (targeting community based audiences);

- Delivering messages over local community radio stations (targeting community based audiences);

- Collaborating with local cultural events to deliver communications through drama, role plays, local dances and speeches by local leaders (targeting community based audiences);

- Holding best practice conferences and learning activities with a range of stakeholders (targeting all national audiences);

- Documenting and disseminating project case studies with identified lessons learned (targeting all audiences);

- Publishing research briefs (targeting national and international audiences); Publishing project results and recommendations reports (targeting national and international audiences).

The underlying approach to the DCI knowledge management strategy will be to develop and disseminate informational messages that are delivered through mechanisms and in formats that are appropriate and accessible for the target audience. This will mean that the manner used to deliver project communications will intentionally vary depending on the particular audience, with feedback loops integrated into communication interventions to ensure that the approach is being well received and understood. Particular emphasis will be placed on engaging a range of actors at the community level

### 3.2.2 Reporting

DCI will deliver two main types of performance reports to its partners

• Quarterly Progress Reports

• Annual Management Report

Apart from the above mentioned performance focused reports, other reporting will be required of DCI implementing partners in the form of monthly report. Monthly reports and biweekly progress reports, among other sources of information will be used in developing the quarterly reports described below. A final report is also required at the end of the project which will summarize results achieved over the Life-of-Project.

Monthly Partner Reports: Implementing Partners will compile a monthly report that will summarize their experiences in the field for the month. The report will contain summaries of activities executed, meetings with project stakeholders, as well as other information relevant to the program. The report will also address any identified problems that require immediate attention by project management. Implementing Partners will submit their monthly reports both narrative and data forms to the M&E Unit and deliver all data capture forms to the M&E unit for collation and analysis.

Quarterly Progress Reports: These will be no longer than 20 pages summarizing: (1) progress to date per the agreed deliverables; (2) identification of specific problems and delays and recommendations for adjustments and corrective action; (3) outcomes of any high-level meetings and field visits; (4) planned activities for the next reporting period; (5) assessment of the validity and efficacy of progress against the Outcomes and Results; (6) progress on gender and environmental compliance; and (7) financial information. The first, second and third quarterly reports are due by the last working day of December, March, June, respectively.

Leads for each IR or project component will synthesize monthly field reports, add their report for the month and submit with a copy to the M&E unit. The M&E unit will then use the data from the monthly and quarterly. Apart from the field reports, component-head reports will capture such information as meetings held with stakeholders’, field visits, supervisory roles, and other project activities undertaken for the reporting period.

Annual Management Report: The fourth quarter progress report will be an Annual Management Report with a descriptive analysis of activities conducted during that fiscal year, a quantitative and/or qualitative description of actual achievements versus planned activities for the year, in both narrative and in data performance table formats. The Annual Report must report against all indicators established in the PMP, and the data performance table will include accomplishments for the fiscal year against that year’s targets.

The summary of data sets will be presented in the indicator-tracking table which will be attached to the report. The preparation of the annual report will be the task of project coordinators with quality assurance by M&E officers. The draft will be circulated for review among project stakeholders before it is finalized and submitted to Programs Director.

## 4.0Role and Responsibilities of the M&E Specialist

- Manage M&E Plan for DCI

- Build capacity of stakeholders and other staff on M&E

- Set up data collection and analysis for projects

- Work with the GIS Specialist to ensure geo-referencing of all PMP data and inclusion into a database and mapping of such data for reporting

- Facilitate learning sessions as part of periodic partner meetings including evaluation of PMP data and implication for meeting performance targets and determining any adjustments that may be needed to improve project performance.

- Work with the entire project team and implementing partners to document project experience, lessons learned and impact of project interventions of status of fish stocks and quality of life of targeted beneficiaries in coastal fishing communities

## 4.1 Role of M&E Officer

- Reports on monthly, quarterly and annual progress on all project activities to the M&E Specialist

- Assists in conducting data collection

- Maintain and update Project’s database (Excel spreadsheet)

- Assist in conducting data quality assessment

M&E Framework

Attached is the M&E Framework for DCI- Ghana Section.